## Estimates
Estimates
This document provides the estimated project costs, resources, and duration
Stages
Staff
Project Documentor,Developer,Manager | Planning | Designing | Developing | Testing | Implementing | Total
| (2 weeks) | (2 weeks) | (3 weeks) | (1 week) | (1 week) | Time
Research Topics | 40 Hours | 1 Hour | 10 Hours | - | - | 51 Hours
-Title | 20 Hours | 30 mins | 5 Hours
-Research Questions | 20 Hours | 30 mins | 5 Hours
Introduction | 1 hour | 2 Hours | 10 Hours | - | - | 13 Hours
-Project Context | 15 mins | 30 mins | 2.5 Hours
-Purpose and Description | 15 mins | 30 mins | 2.5 Hours
-Objectives | 15 mins | 30 mins | 2.5 Hours
-Scope and Limitations | 15 mins | 30 mins | 2.5 Hours
Related Literature | 5 hours | 2 Hour | 10 Hours | - | - | 17 Hours
Abstract | 30 mins | 3 Hour | 10 Hours | - | - | 43 Hours
Technical Background | 30 mins | 4 Hours | 10 Hours | - | - | 44 Hours
Design and Methodology | 40 Hours | 4 Hour | 10 Hours | - | - | 54 Hours
WBS | 2 Hours | 1 Hour | 1 Hour | - | - | 4 Hours
Tasks | 2 Hours | 1 Hour | 1 Hour | - | - | 4 Hours
Gantt Chart | 2 Hours | 1 Hour | 1 Hour | - | - | 4 Hours
Diagrams | 40 Hours | 40 Hours | 40 Hours | - | - | 120 Hours
SRS | 2 Hours | 1 Hour | 1 Hour | - | - | 4 Hours
Vision and Scope Document | 3 Hours | 3 Hours | 1 Hour | - | - | 7 Hours
Scope of Work | 1 Hour | 1 Hour | 1 Hour | - | - | 3 Hours
Estimates | 3 Hours | 3 Hours | 3 Hours | - | - | 9 Hours
Prototype | 10 Hours | 10 Hours | 40 Hours | 5 Hours | - | 65 Hours
[5 empty] | Total | 442 Hours